## Yr 2 Expenditure Report
YEAR 2 EXPENDITURE REPORT
Form revised: September 2015
| Variance from | Approved Budget | Actual Expenditures | Actual Expenditures | Variance | Variance Percentage (%) | 7. Please Briefly Explain Any Variance | 8. Total (Overall) Project Budget | 9. Total (Overall) Project Actual Expenditures
| Year 1 | Year 2 | Year 2 | Year 2 COVID Program | Year 2 | Year 2 | Greater Than 15% Or $25,000 | Year 2 | Year 2
Personnel
Tanzania Local Staff
Salaries | 2899.7129 | 55940 | 97188.8 | 10301.57 | -38349.0871 | -65.18% | Project was extended due to Covid 19 activities approval delay by the government , this has caused some additional personnel costs | 72930.0529 | 121580.71
Tanzania Expatriate and TCN Staff
Salaries | 2461.92 | 1280 | 7841.32 | 0 | -4099.4 | -109.6% | Project was extended due to Covid 19 activities approval delay by the government , this has caused some additional personnel costs | 3741.92 | 7841.32
Home Office Staff
Salaries | 11011.05 | 21419 | 40011.7 | 0 | -7581.65 | -23.38% | Project was extended due to Covid 19 activities approval delay by the government , this has caused some additional personnel costs | 34401.92 | 41983.57
US Program Support Costs* | 4828.1127 | 1214.3928 | 0 | 0 | 6042.5055 | 100% | NA | 6042.5055 | 0
Allowances | 2974.3 | 1548.5412 | 9069.67 | 0 | -4546.8288 | -100.5% | Project was extended due to Covid 19 activities approval delay by the government , this has caused some additional personnel costs | 4556.1012 | 9102.93
Tanzania Fringe | 815.8959 | 13230.3 | 29851.41 | 2373.53 | -15805.2141 | -112.5% | Project was extended due to Covid 19 activities approval delay by the government , this has caused some additional personnel costs | 18327.3159 | 36506.06
Home Office, Expat & TCN Fringe | 3150.4553 | 9100.763 | 17997.68 | 0 | -5746.4617 | -46.91% | Project was extended due to Covid 19 activities approval delay by the government , this has caused some additional personnel costs | 13170.4783 | 18916.94
0
Subtotal Personnel | 28141.4468 | 103732.997 | 201960.58 | 12675.1 | -70086.1361 | -53.15% |  | 153170.2939 | 235931.53
Non-Personnel
Travel | 32872.8 | 12600.325 | 22986.4 | 0 | 22486.725 | 49.45% | Due to COVID 19 pandemic, project team could not travel to the field as it was initially planned. The fund was reallocated to other budget lines | 45707.325 | 23220.6
Supplies & Materials | 130643.9998 | 0 | 18079.1717 | 94064.31 | 112564.828 | 86.16% | All PPE materials were procured as planned | 156334.5898 | 137834.0717
Trainings and Events | 201447.4603 | 24536.2432 | 130403.01 | 495.84 | 95580.6935 | 42.3% |  | 228753.8835 | 133669.03
Other Program Costs* | 3762.1513 | 0 | 11592.0978 | 0 | -7829.9465 | -208.1% | Jennifer please can you help to respond to this line as it related to EGPAF HQ? | 5589.647 | 13419.5935
IRB Fees and Publication Costs | 4240 | 0 | 100 | 0 | 4140 | 97.64% | N/A | 4240 | 100
Books, Dues & Subscriptions | -0.86 | 0 | 57.58 | 0 | -58.44 | 6795% | During planing there was no planned shared costs but during implementation these shared costs were supposed to be covered by the project according to original cost share agreement | 0 | 58.44
Data/Communications | -3.05 | 0 | 2024.43 | 0 | -2027.48 | 66475% | During planing there was no planned shared costs but during implementation these shared costs were supposed to be covered by the project according to original cost share agreement | 0 | 2027.48
Insurance: Business Liability | -120.22 | 0 | 858.43 | 0 | -978.65 | 814% | During planing there was no planned shared costs but during implementation these shared costs were supposed to be covered by the project according to original cost share agreement | 0 | 978.65
Equipment & Furn Rental | -2.2 | 0 | 232.94 | 0 | -235.14 | 10688% | During planing there was no planned shared costs but during implementation these shared costs were supposed to be covered by the project according to original cost share agreement | 0 | 235.14
Staff Recruiting | 0 | 0 | 0 | 0 | 0 |  | During planing there was no planned shared costs but during implementation these shared costs were supposed to be covered by the project according to original cost share agreement | 0 | 0
Conf & Training - Registration | 0 | 0 | 13.48 | 0 | -13.48 |  | During planing there was no planned shared costs but during implementation these shared costs were supposed to be covered by the project according to original cost share agreement | 0 | 13.48
Repairs & Maintenance | -447.91 | 0 | 2860.16 | 0 | -3308.07 | 738.6% | During planing there was no planned shared costs but during implementation these shared costs were supposed to be covered by the project according to original cost share agreement | 0 | 3308.07
Fuel & Oil | 0 | 0 | 1684.24 | 0 | -1684.24 |  | During planing there was no planned shared costs but during implementation these shared costs were supposed to be covered by the project according to original cost share agreement | 0 | 1684.24
Postage & Shipping | -0.45 | 0 | 2656.64 | 3348.03 | -2657.09 | 590464% | During planing there was no planned shared costs but during implementation these shared costs were supposed to be covered by the project according to original cost share agreement | 0 | 6005.12
Rent | -821.26 | 0 | 4859.61 | 0 | -5680.87 | 691.7% | During planing there was no planned shared costs but during implementation these shared costs were supposed to be covered by the project according to original cost share agreement | 0 | 5680.87
Rent: Storage & Utilities | -205.83 | 0 | 2007.55 | 0 | -2213.38 | 1075% | During planing there was no planned shared costs but during implementation these shared costs were supposed to be covered by the project according to original cost share agreement | 0 | 2213.38
Telephone & Fax | -0.21 | 0 | 1403.88 | 0 | -1404.09 | 668614% | During planing there was no planned shared costs but during implementation these shared costs were supposed to be covered by the project according to original cost share agreement | 0 | 1404.09
Bank & Merchant Fees | -137.18 | 0 | 1323.45 | 0 | -1460.63 | 1065% | During planing there was no planned shared costs but during implementation these shared costs were supposed to be covered by the project according to original cost share agreement | 0 | 1460.63
Legal and Translation Services | 0 | 0 | 286.96 | 0 | -286.96 |  | During planing there was no planned shared costs but during implementation these shared costs were supposed to be covered by the project according to original cost share agreement | 0 | 286.96
Staff Meeting | -7.95 | 0 | 18.15 | 0 | -26.1 | 328.3% | During planing there was no planned shared costs but during implementation these shared costs were supposed to be covered by the project according to original cost share agreement | 0 | 26.1
VAT Charges | -5015.94 | 0 | 9882.68 | 1927.83 | -14898.62 | 297% | During planing there was no planned shared costs but during implementation these shared costs were supposed to be covered by the project according to original cost share agreement | 0 | 16826.45
Other | 0 | 0 | 10156.95 | 951.69 | -10156.95 |  | During planing there was no planned shared costs but during implementation these shared costs were supposed to be covered by the project according to original cost share agreement | 0 | 11108.64
Subtotal Non-Personnel | 366203.3514 | 37136.5682 | 223487.8096 | 100787.7 | 179852.1101 | 44.59% |  | 440625.4453 | 361561.0352
Total Personnel & Non-Personnel | 394344.7983 | 140869.5652 | 425448.3896 | 113462.8 | 109765.9739 | 20.51% |  | 593795.7391 | 597492.5652
Indirect Costs |  |  |  | 0
Other
Consultants | 6676.57 | 0 | 9730.17 | 204.87 | -3053.6 | -45.74% |  | 7135 | 10393.47
Sub award | 86447.53 | 0 | 78937.71 | 0 | 7509.82 | 8.687% |  | 99999.9 | 92490.08
0
0
Total Other | 93124.1 | 0 | 88667.88 | 204.87 | 4456.22 | 4.785% |  | 107134.9 | 102883.55
GRAND TOTAL
* An allocation of costs representing the balance of US program personnel costs that EGPAF normally bills as indirect costs.
10. Other Funding Sources for Project
| Year 1 | Year 2 | Year 3 |  | TOTAL
Committed
Name the source |  |  |  |  | 0
Name the source |  |  |  |  | 0
Name the source |  |  |  |  | 0
Name the source |  |  |  |  | 0
Name the source |  |  |  |  | 0
Name the source |  |  |  |  | 0
Name the source |  |  |  |  | 0
Name the source |  |  |  |  | 0
Total Committed | 0 | 0 | 0 |  | 0
Projected
Name the source |  |  |  |  | 0
Name the source |  |  |  |  | 0
Name the source |  |  |  |  | 0
Name the source |  |  |  |  | 0
Name the source |  |  |  |  | 0
Name the source |  |  |  |  | 0
Name the source |  |  |  |  | 0
Name the source |  |  |  |  | 0
Total Projected | 0 | 0 | 0 |  | 0
GRAND TOTAL | 0 | 0 | 0 |  | 0
Organization Name: Elizabeth Glaser Pediatric AIDS Foundation
Grant Number:
Grant Period: April 1, 2020 - September 30, 2021
Report Period: April 1, 2020 - September 30, 2021
1. Prepared By:
2. Title:
3. Email:
4. Phone: None
5. Date Prepared: November 30, 2021
7. Please Briefly Explain Any Variance Greater Than 15% Or $25,000 (additional space):

## Yr 3 Expenditure Report (hidden)
Hilton Foundation - YEAR 3 EXPENDITURE REPORT
Form revised: September 2015
| Hilton Foundation Variance from | Hilton Foundation Approved Budget | 6. Hilton Foundation Actual Expenditures | Variance | Variance Percentage (%) | 7. Please Briefly Explain Any Variance | 8. Total (Overall) Project Budget | 9. Total (Overall) Project Actual Expenditures
| Year 2 | Year 3 | Year 3 | Year 3 | Year 3 | Greater Than 15% Or $25,000 | Year 3 | Year 3
Personnel
Position (% FTE) |  |  |  | 0 | #DIV/0!
Position (% FTE) |  |  |  | 0 | #DIV/0!
Position (% FTE) |  |  |  | 0 | #DIV/0!
Position (% FTE) |  |  |  | 0 | #DIV/0!
Position (% FTE) |  |  |  | 0 | #DIV/0!
Benefits |  |  |  | 0 | #DIV/0!
Taxes |  |  |  | 0 | #DIV/0!
Subtotal Personnel | 0 | 0 | 0 | 0 | #DIV/0! |  | 0 | 0
Non-Personnel
Conferences, Meetings & Trainings |  |  |  | 0 | #DIV/0!
Evaluation |  |  |  | 0 | #DIV/0!
Printing & Postage |  |  |  | 0 | #DIV/0!
Rent |  |  |  | 0 | #DIV/0!
Staff Travel & Transportation |  |  |  | 0 | #DIV/0!
Supplies & Materials |  |  |  | 0 | #DIV/0!
Telephone & Internet |  |  |  | 0 | #DIV/0!
Other: |  |  |  | 0 | #DIV/0!
Other: |  |  |  | 0 | #DIV/0!
Subtotal Non-Personnel | 0 | 0 | 0 | 0 | #DIV/0! |  | 0
Total Personnel & Non-Personnel | 0 | 0 | 0 | 0 | #DIV/0! |  | 0
Indirect Costs |  |  |  | 0 | #DIV/0!
Other
Consultants |  |  |  | 0 | #DIV/0!
Sub-Grants to Other Organizations |  |  |  | 0 | #DIV/0!
Equipment |  |  |  | 0 | #DIV/0!
Other: |  |  |  | 0 | #DIV/0!
Total Other | 0 | 0 | 0 | 0 | #DIV/0! |  | 0 | 0
GRAND TOTAL | 0 | 0 | 0 | 0 | #DIV/0! |  | 0 | 0
10. Other Funding Sources for Project
| Year 1 | Year 2 | Year 3 | TOTAL
Committed
Name the source |  |  |  | 0
Name the source |  |  |  | 0
Name the source |  |  |  | 0
Name the source |  |  |  | 0
Name the source |  |  |  | 0
Name the source |  |  |  | 0
Name the source |  |  |  | 0
Name the source |  |  |  | 0
Total Committed | 0 | 0 | 0 | 0
Projected
Name the source |  |  |  | 0
Name the source |  |  |  | 0
Name the source |  |  |  | 0
Name the source |  |  |  | 0
Name the source |  |  |  | 0
Name the source |  |  |  | 0
Name the source |  |  |  | 0
Name the source |  |  |  | 0
Total Projected | 0 | 0 | 0 | 0
GRAND TOTAL | 0 | 0 | 0 | 0
Organization Name: Enter Name
Grant Number: Enter Grant Number
Grant Period: Enter Start Date - End Date
Report Period: Enter Start Date - End Date
1. Prepared By: Enter Name
2. Title: Enter Title
3. Email: Enter Email Address
4. Phone: Enter Complete Phone #, including country code if outside of U.S.
5. Date Prepared: Enter Date
7. Please Briefly Explain Any Variance Greater Than 15% Or $25,000 (additional space):

## Budget - Revision (xx-xx-xx) (hidden)
Hilton Foundation - BUDGET FORM - MODIFICATION
Form revised: September 2015
| 6. Total (Overall) Project Budget | Hilton Foundation Approved Budget | 7. Hilton Foundation Requested Budget Modification | 8. Please Briefly Explain The Budget Modification Requested
| Year 1 | Year 1 | Year 1
Start Date | Mo/Day/Yr | Mo/Day/Yr | Mo/Day/Yr
End Date | Mo/Day/Yr | Mo/Day/Yr | Mo/Day/Yr
Personnel
Position (% FTE)
Position (% FTE)
Position (% FTE)
Position (% FTE)
Position (% FTE)
Benefits
Taxes
Subtotal Personnel | 0 | 0 | 0
Non-Personnel
Conferences, Meetings & Trainings
Evaluation
Printing & Postage
Rent
Staff Travel & Transportation
Supplies & Materials
Telephone & Internet
Other:
Other:
Subtotal Non-Personnel | 0 | 0 | 0
Total Personnel & Non-Personnel | 0 | 0 | 0
Indirect Costs (see instructions) @ ____ %
Other
Consultants
Sub-Grants to Other Organizations
Equipment
Other:
Total Other | 0 | 0 | 0
GRAND TOTAL | 0 | 0 | 0
9. Other Funding
Sources for Project
Year 1
Committed
Name the source
Name the source
Name the source
Name the source
Name the source
Name the source
Name the source
Name the source
Total Committed | 0
Projected
Name the source
Name the source
Name the source
Name the source
Name the source
Name the source
Name the source
Name the source
Total Projected | 0
GRAND TOTAL | 0
Organization Name: Enter Name
Grant Number: Enter Grant Number
Grant Period: Enter Start Date - End Date
1. Prepared By: Enter Name
2. Title: Enter Title
3. Email: Enter Email Address
4. Phone: Enter Complete Phone #, including country code if outside of U.S.
5. Date Prepared: Enter Date
8. Please Briefly Explain The Budget Modification Requested (additional space):